## Registration QA Report
KANAKU - USER REGISTRATION FEATURE QA VALIDATION REPORT
Test Case ID | Test Category | Scenario / Description | Prerequisites | Test Data | Expected Result | Actual Result | Status
TC-REG-UI-01 | UI Testing | Happy path: complete registration flow on UI and redirects to onboarding | No active session, Dev server running | firstName: Dynamic, lastName: Dynamic, email: Dynamic, mobile: Dynamic, password: Password123! | Account created successfully, user is logged in, and onboarding flow is shown. | User successfully registered, token saved in local storage, redirected to onboarding flow. | PASS
TC-REG-UI-02 | UI Testing | UI Validation: blocks registration with invalid email format | Dev server running | firstName: Dynamic, lastName: Dynamic, email: not-an-email, mobile: Dynamic, password: Password123! | Submit button is disabled, inline error 'Invalid email address' is displayed. | Submit button was disabled, inline error displayed under Email Address field. | PASS
TC-REG-UI-03 | UI Testing | UI Validation: blocks registration with mismatched passwords | Dev server running | email: Dynamic, password: Password123!, confirmPassword: DifferentPassword123! | Submit button is disabled, mismatched password warning is shown. | Submit button remained disabled due to password validation mismatch. | PASS
TC-REG-UI-04 | UI Testing | UI Validation: blocks registration when terms are unchecked | Dev server running | All valid inputs, terms checkbox: unchecked | Submit button is disabled. | Submit button remained disabled until terms checkbox was checked. | PASS
TC-REG-UI-05 | UI Testing | UI Validation: duplicate email is blocked with generic message, no success screen | Dev server running, email already registered | email: existing_user@kanaku.test | Inline error 'This email can't be used for a new account' is displayed on blur; submit disabled. | Email blur triggered unique email check, showing generic inline rejection, submit button disabled. | PASS
TC-REG-API-01 | API Testing | registers a new user successfully and creates DB records (201) | Prisma client initialized | name: Dynamic, email: Dynamic, password: Password123!, mobile: Dynamic | Returns HTTP 201 Created with JSON response containing user object, access token, and refresh token cookie. | HTTP 201 returned with correct JSON structure, user record written to DB. | PASS
TC-REG-API-02 | API Testing | rejects duplicate email with 409 Conflict | Email already exists in database | email: existing_user@kanaku.test | Returns HTTP 409 Conflict with EMAIL_EXISTS error code. | HTTP 409 Conflict returned with EMAIL_EXISTS code. | PASS
TC-REG-API-03 | API Testing | rejects duplicate mobile/phone with 409 Conflict | Phone already exists in database | mobile: 9999999999 | Returns HTTP 409 Conflict with PHONE_EXISTS error code. | HTTP 409 Conflict returned with PHONE_EXISTS code. | PASS
TC-REG-API-04 | API Testing | rejects validation scenario: Empty Email | Dev server running | email: '' | Returns HTTP 400 Bad Request with validation error code. | HTTP 400 Bad Request returned with validation details. | PASS
TC-REG-API-05 | API Testing | rejects validation scenario: Invalid Email Format | Dev server running | email: invalid-format | Returns HTTP 400 Bad Request with validation error code. | HTTP 400 Bad Request returned with validation details. | PASS
TC-REG-API-06 | API Testing | rejects validation scenario: Missing Name | Dev server running | name: absent/empty | Returns HTTP 400 Bad Request with validation error code. | HTTP 400/Bad Request returned. | PASS
TC-REG-API-07 | API Testing | rejects validation scenario: Short Password | Dev server running | password: short | Returns HTTP 400 Bad Request with validation error code. | HTTP 400/Bad Request returned. | PASS
TC-REG-API-08 | API Testing | rejects validation scenario: Weak Password - No special chars | Dev server running | password: WeakPassword123 | Returns HTTP 400 Bad Request with validation error code. | HTTP 400/Bad Request returned. | PASS
TC-REG-API-09 | API Testing | rejects validation scenario: Weak Password - No uppercase | Dev server running | password: weakpassword123! | Returns HTTP 400 Bad Request with validation error code. | HTTP 400/Bad Request returned. | PASS
TC-REG-API-10 | API Testing | rejects validation scenario: Weak Password - No digits | Dev server running | password: WeakPassword! | Returns HTTP 400 Bad Request with validation error code. | HTTP 400/Bad Request returned. | PASS
TC-REG-API-11 | API Testing | sanitizes and processes Name with SQL Injection payload safely | Dev server running | name: ' OR '1'='1 | Returns HTTP 201 Created. DB stores raw payload safely without executing the injection. | HTTP 201 returned. Name stored as literal string in database, verified secure. | PASS
TC-REG-API-12 | API Testing | processes Name with XSS payload safely by stripping scripts | Dev server running | name: QA User <script>alert("xss")</script> | Returns HTTP 201 Created. Script tags are stripped from the name attribute before writing to DB. | HTTP 201 returned. Script tag stripped, name saved as 'QA User' in database. | PASS
TC-REG-DB-01 | Database Validation | verifies registration inputs correctly map to DB tables and reflect in profile endpoints | Unique user credentials | All registration parameters | Rows added to User, profiles, UserSettings, and default Account tables with correct matching values. | All database tables verify exact column mapping and correct relation constraints. | PASS
TC-REG-FPS-01 | Forgot Password | happy path: request OTP, verify and reset password successfully | Registered user exists | email: Dynamic, newPassword: NewCoolPassword123! | User can request OTP, verify it, reset password, and log in with new password. Old password is deleted. | Reset OTP requested, verified, password updated to new hashed value, login successful. | PASS